## SUMMARY
SDR – SPECIFICATION DEVIATION REQUEST ¦ COMP5 PROJECT SUMMARY
Report Date: 28 June 2026
SDR ISSUED (by Sai) | SDR NOT REPLIED (Not Expired) | SDR NOT REPLIED (Expired) | SDR REPLIED CLOSED | SDR REPLIED OPEN
17 | 1 | 10 | 5 | 1
DISCIPLINE BREAKDOWN
Discipline | ISSUED (by Sai) | NOT REPLIED (Not Exp.) | NOT REPLIED (Expired) | REPLIED CLOSED | REPLIED OPEN
Corrosion Engineering | 3 | 1 | 0 | 2 | 0
Electrical | 2 | 0 | 1 | 0 | 1
Instrumentation | 1 | 0 | 1 | 0 | 0
Material Technology | 1 | 0 | 0 | 1 | 0
Piping | 2 | 0 | 0 | 2 | 0
HSE&Q/LOSPE | 1 | 0 | 1 | 0 | 0
Structural | 5 | 0 | 5 | 0 | 0
Telecommunications | 2 | 0 | 2 | 0 | 0
TOTAL | 17 | 1 | 10 | 5 | 1
⚠ EXPIRED — URGENT ACTION REQUIRED
# | Document Number | Document Title | Discipline | Engineer | Date Issued to CPY | Due Date | Days Overdue
1 | COMP5-SPM-EL-SDR-00012 | SPECIFICATION DEVIATION REQUEST FOR MINIMUM SEPARATION BETWEEN CABLES | EL | Munjuluru Kiran Kumar | 16-Apr-2026 | 06-May-2026 | OVERDUE 53d
2 | COMP5-SPM-IN-SDR-00024 | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION OF FUEL GAS METERING SYSTEM AND FEED INSTRUMENT AND CONTROL SYSTEM DESIGN BASIS TO UTILIZE PROJECT AVL FOR TUBING AND FITTINGS | IN | Sadasivam Pradeep | 03-Jun-2026 | 23-Jun-2026 | OVERDUE 5d
3 | COMP5-SPM-SH-SDR-00008 | SPECIFICATION DEVIATION REQUEST FOR CLEAN AGENT FIRE SUPPRESSION SYSTEM PROTECTION FOR FIREWATER PUMP ENCLOSURE | SH | Alam Mohammed Tanveer | 08-May-2026 | 28-May-2026 | OVERDUE 31d
4 | COMP5-SPM-ST-SDR-00003 | SPECIFICATION DEVIATION REQUEST FOR STRUCTURE TOUGHNESS CLASS TEMPERATURE DEFINITION | ST | Andoko Wijayanto | 21-Apr-2026 | 11-May-2026 | OVERDUE 48d
5 | COMP5-SPM-ST-SDR-00014 | SPECIFICATION DEVIATION REQUEST FOR USE OF PULTRUDED TYPE GRATING INSTEAD OF MOLDED GRATING | ST | Govindarajan Amudharajan | 04-May-2026 | 24-May-2026 | OVERDUE 35d
6 | COMP5-SPM-ST-SDR-00020 | SPECIFICATION DEVIATION REQUEST FOR RELAXATION OF ROLLING DIRECTION REQUIREMENT | ST | Andrea Mariani | 18-May-2026 | 07-Jun-2026 | OVERDUE 21d
7 | COMP5-SPM-ST-SDR-00021 | SPECIFICATION DEVIATION REQUEST FOR MOORING BITTS AVOIDANCE FOR TRIPODS | ST | Andrea Mariani | 18-May-2026 | 07-Jun-2026 | OVERDUE 21d
8 | COMP5-SPM-ST-SDR-00022 | SPECIFICATION DEVIATION REQUEST FOR SUBSTITUTING PILES DRIFT TEST WITH ACCURATE DC REPORTS | ST | Andrea Mariani | 18-May-2026 | 07-Jun-2026 | OVERDUE 21d
9 | COMP5-SPM-TC-SDR-00018 | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION DEVIATION REQUEST FOR PUSH BUTTON REQUIREMENT ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | TC | Mohammed Abdul Shadab Ahmer | 02-Jun-2026 | 22-Jun-2026 | OVERDUE 6d
10 | COMP5-SPM-TC-SDR-00019 | SPECIFICATION DEVIATION REQUEST FOR AUTOMATIC TRANSFER SWITCH ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | TC | Gurunathan Sathish Nathan | 02-Jun-2026 | 22-Jun-2026 | OVERDUE 6d

## SDR ISSUED (by Sai)
SDR ISSUED (BY SAI) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 17 ¦ SDR ISSUED (by Sai) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response
1 | CE | COMP5-SPM-CE-SDR-00001 | C | SPECIFICATION DEVIATION REQUEST FOR PROCUREMENT PHILOSOPHY OF CS CLAD PIPES |  |  | COMP5-T-SPM-QELNG-00088 | 19-Mar-2026 | 08-Apr-2026 | COMP5-T-QELNG-SPM-00081 | 30-Mar-2026 | A-Approved/Reviewed with no comments
2 | CE | COMP5-SPM-CE-SDR-00007 | B | SPECIFICATION DEVIATION REQUEST FOR HYDROTEST AFTER OVERLAYING (CLADDED PIPES) | Venkateswaran Viswanathan | 26-Mar-2026 | COMP5-T-SPM-QELNG-00184 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00301 | 04-May-2026 | A-Approved/Reviewed with no comments
3 | CE | COMP5-SPM-CE-SDR-00027 | B | SPECIFICATION DEVIATION REQUEST FOR APPLICATION OF PAUT ON WELD SEAM IN LIEU OF RT FOR PIPE WALL THICKNESS OF MIN 45MM | Mihai Marius | 22-Jun-2026 | COMP5-T-SPM-QELNG-01070 | 23-Jun-2026 | 13-Jul-2026
4 | EL | COMP5-SPM-EL-SDR-00010 | B | SPECIFICATION DEVIATION REQUEST FOR ELECTRICAL - SLD & SCHEMATICS DRAWING USING AUTOCAD | Vellapandian Kulasekaran | 07-Apr-2026 | COMP5-T-SPM-QELNG-00270 | 10-Apr-2026 | 30-Apr-2026 | COMP5-T-QELNG-SPM-00683 | 17-Jun-2026 | B-Approved/Reviewed with minor comments
5 | EL | COMP5-SPM-EL-SDR-00012 | B | SPECIFICATION DEVIATION REQUEST FOR MINIMUM SEPARATION BETWEEN CABLES | Munjuluru Kiran Kumar | 08-Apr-2026 | COMP5-T-SPM-QELNG-00330 | 16-Apr-2026 | 06-May-2026
6 | IN | COMP5-SPM-IN-SDR-00024 | B | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION OF FUEL GAS METERING SYSTEM AND FEED INSTRUMENT AND CONTROL SYSTEM DESIGN BASIS TO UTILIZE PROJECT AVL FOR TUBING AND FITTINGS | Sadasivam Pradeep | 02-Jun-2026 | COMP5-T-SPM-QELNG-00771 | 03-Jun-2026 | 23-Jun-2026
7 | MT | COMP5-SPM-MT-SDR-00013 | B | SPECIFICATION DEVIATION REQUEST FOR WELD OVERLAY REPAIRS AT COMPONENT ENDS | Venkateswaran Viswanathan | 09-Apr-2026 | COMP5-T-SPM-QELNG-00276 | 10-Apr-2026 | 30-Apr-2026 | COMP5-T-QELNG-SPM-00371 | 13-May-2026 | A-Approved/Reviewed with no comments
8 | PI | COMP5-SPM-PI-SDR-00002 | B | SPECIFICATION DEVIATION REQUEST FOR INCONEL 625 WELDED PIPES – DEVIATION ON USING FILLER METAL IN THE PRODUCTION OF ALLOY 625 PIPES | Dolly Maria Mathew | 10-Mar-2026 | COMP5-T-SPM-QELNG-00101 | 24-Mar-2026 | 13-Apr-2026 | COMP5-T-QELNG-SPM-00176 | 20-Apr-2026 | A-Approved/Reviewed with no comments
9 | PI | COMP5-SPM-PI-SDR-00004 | B | SPECIFICATION DEVIATION REQUEST FOR HYDROTESTING PRESSURE OF PIPES AT MANUFACTURER’S SHOP | Dolly Maria Mathew | 10-Mar-2026 | COMP5-T-SPM-QELNG-00101 | 24-Mar-2026 | 13-Apr-2026 | COMP5-T-QELNG-SPM-00176 | 20-Apr-2026 | A-Approved/Reviewed with no comments
10 | SH | COMP5-SPM-SH-SDR-00008 | B | SPECIFICATION DEVIATION REQUEST FOR CLEAN AGENT FIRE SUPPRESSION SYSTEM PROTECTION FOR FIREWATER PUMP ENCLOSURE | Alam Mohammed Tanveer | 31-Mar-2026 | COMP5-T-SPM-QELNG-00586 | 08-May-2026 | 28-May-2026
11 | ST | COMP5-SPM-ST-SDR-00003 | B | SPECIFICATION DEVIATION REQUEST FOR STRUCTURE TOUGHNESS CLASS TEMPERATURE DEFINITION | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00377 | 21-Apr-2026 | 11-May-2026
12 | ST | COMP5-SPM-ST-SDR-00014 | B | SPECIFICATION DEVIATION REQUEST FOR USE OF PULTRUDED TYPE GRATING INSTEAD OF MOLDED GRATING | Govindarajan Amudharajan | 14-Apr-2026 | COMP5-T-SPM-QELNG-00519 | 04-May-2026 | 24-May-2026
13 | ST | COMP5-SPM-ST-SDR-00020 | B | SPECIFICATION DEVIATION REQUEST FOR RELAXATION OF ROLLING DIRECTION REQUIREMENT | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026
14 | ST | COMP5-SPM-ST-SDR-00021 | B | SPECIFICATION DEVIATION REQUEST FOR MOORING BITTS AVOIDANCE FOR TRIPODS | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026
15 | ST | COMP5-SPM-ST-SDR-00022 | B | SPECIFICATION DEVIATION REQUEST FOR SUBSTITUTING PILES DRIFT TEST WITH ACCURATE DC REPORTS | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026
16 | TC | COMP5-SPM-TC-SDR-00018 | B | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION DEVIATION REQUEST FOR PUSH BUTTON REQUIREMENT ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | Mohammed Abdul Shadab Ahmer | 03-May-2026 | COMP5-T-SPM-QELNG-00760 | 02-Jun-2026 | 22-Jun-2026
17 | TC | COMP5-SPM-TC-SDR-00019 | B | SPECIFICATION DEVIATION REQUEST FOR AUTOMATIC TRANSFER SWITCH ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | Gurunathan Sathish Nathan | 07-May-2026 | COMP5-T-SPM-QELNG-00760 | 02-Jun-2026 | 22-Jun-2026

## SDR NOT REPLIED (Not Expired)
SDR NOT REPLIED (NOT EXPIRED) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 1 ¦ SDR NOT REPLIED (Not Expired) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Days Remaining
1 | CE | COMP5-SPM-CE-SDR-00027 | B | SPECIFICATION DEVIATION REQUEST FOR APPLICATION OF PAUT ON WELD SEAM IN LIEU OF RT FOR PIPE WALL THICKNESS OF MIN 45MM | Mihai Marius | 22-Jun-2026 | COMP5-T-SPM-QELNG-01070 | 23-Jun-2026 | 13-Jul-2026 |  |  |  | 15 days

## SDR NOT REPLIED (Expired)
SDR NOT REPLIED (EXPIRED) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 10 ¦ SDR NOT REPLIED (Expired) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Days Remaining
1 | EL | COMP5-SPM-EL-SDR-00012 | B | SPECIFICATION DEVIATION REQUEST FOR MINIMUM SEPARATION BETWEEN CABLES | Munjuluru Kiran Kumar | 08-Apr-2026 | COMP5-T-SPM-QELNG-00330 | 16-Apr-2026 | 06-May-2026 |  |  |  | OVERDUE 53d
2 | IN | COMP5-SPM-IN-SDR-00024 | B | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION OF FUEL GAS METERING SYSTEM AND FEED INSTRUMENT AND CONTROL SYSTEM DESIGN BASIS TO UTILIZE PROJECT AVL FOR TUBING AND FITTINGS | Sadasivam Pradeep | 02-Jun-2026 | COMP5-T-SPM-QELNG-00771 | 03-Jun-2026 | 23-Jun-2026 |  |  |  | OVERDUE 5d
3 | SH | COMP5-SPM-SH-SDR-00008 | B | SPECIFICATION DEVIATION REQUEST FOR CLEAN AGENT FIRE SUPPRESSION SYSTEM PROTECTION FOR FIREWATER PUMP ENCLOSURE | Alam Mohammed Tanveer | 31-Mar-2026 | COMP5-T-SPM-QELNG-00586 | 08-May-2026 | 28-May-2026 |  |  |  | OVERDUE 31d
4 | ST | COMP5-SPM-ST-SDR-00003 | B | SPECIFICATION DEVIATION REQUEST FOR STRUCTURE TOUGHNESS CLASS TEMPERATURE DEFINITION | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00377 | 21-Apr-2026 | 11-May-2026 |  |  |  | OVERDUE 48d
5 | ST | COMP5-SPM-ST-SDR-00014 | B | SPECIFICATION DEVIATION REQUEST FOR USE OF PULTRUDED TYPE GRATING INSTEAD OF MOLDED GRATING | Govindarajan Amudharajan | 14-Apr-2026 | COMP5-T-SPM-QELNG-00519 | 04-May-2026 | 24-May-2026 |  |  |  | OVERDUE 35d
6 | ST | COMP5-SPM-ST-SDR-00020 | B | SPECIFICATION DEVIATION REQUEST FOR RELAXATION OF ROLLING DIRECTION REQUIREMENT | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026 |  |  |  | OVERDUE 21d
7 | ST | COMP5-SPM-ST-SDR-00021 | B | SPECIFICATION DEVIATION REQUEST FOR MOORING BITTS AVOIDANCE FOR TRIPODS | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026 |  |  |  | OVERDUE 21d
8 | ST | COMP5-SPM-ST-SDR-00022 | B | SPECIFICATION DEVIATION REQUEST FOR SUBSTITUTING PILES DRIFT TEST WITH ACCURATE DC REPORTS | Andrea Mariani |  | COMP5-T-SPM-QELNG-00668 | 18-May-2026 | 07-Jun-2026 |  |  |  | OVERDUE 21d
9 | TC | COMP5-SPM-TC-SDR-00018 | B | SPECIFICATION DEVIATION REQUEST FOR SPECIFICATION DEVIATION REQUEST FOR PUSH BUTTON REQUIREMENT ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | Mohammed Abdul Shadab Ahmer | 03-May-2026 | COMP5-T-SPM-QELNG-00760 | 02-Jun-2026 | 22-Jun-2026 |  |  |  | OVERDUE 6d
10 | TC | COMP5-SPM-TC-SDR-00019 | B | SPECIFICATION DEVIATION REQUEST FOR AUTOMATIC TRANSFER SWITCH ON FEED SPECIFICATION FOR TELECOMMUNICATION SYSTEMS, 200-52-TC-SPC-00001 | Gurunathan Sathish Nathan | 07-May-2026 | COMP5-T-SPM-QELNG-00760 | 02-Jun-2026 | 22-Jun-2026 |  |  |  | OVERDUE 6d

## SDR REPLIED CLOSED
SDR REPLIED CLOSED ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 5 ¦ SDR REPLIED CLOSED ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response
1 | CE | COMP5-SPM-CE-SDR-00001 | C | SPECIFICATION DEVIATION REQUEST FOR PROCUREMENT PHILOSOPHY OF CS CLAD PIPES |  |  | COMP5-T-SPM-QELNG-00088 | 19-Mar-2026 | 08-Apr-2026 | COMP5-T-QELNG-SPM-00081 | 30-Mar-2026 | A-Approved/Reviewed with no comments
2 | CE | COMP5-SPM-CE-SDR-00007 | B | SPECIFICATION DEVIATION REQUEST FOR HYDROTEST AFTER OVERLAYING (CLADDED PIPES) | Venkateswaran Viswanathan | 26-Mar-2026 | COMP5-T-SPM-QELNG-00184 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00301 | 04-May-2026 | A-Approved/Reviewed with no comments
3 | MT | COMP5-SPM-MT-SDR-00013 | B | SPECIFICATION DEVIATION REQUEST FOR WELD OVERLAY REPAIRS AT COMPONENT ENDS | Venkateswaran Viswanathan | 09-Apr-2026 | COMP5-T-SPM-QELNG-00276 | 10-Apr-2026 | 30-Apr-2026 | COMP5-T-QELNG-SPM-00371 | 13-May-2026 | A-Approved/Reviewed with no comments
4 | PI | COMP5-SPM-PI-SDR-00002 | B | SPECIFICATION DEVIATION REQUEST FOR INCONEL 625 WELDED PIPES – DEVIATION ON USING FILLER METAL IN THE PRODUCTION OF ALLOY 625 PIPES | Dolly Maria Mathew | 10-Mar-2026 | COMP5-T-SPM-QELNG-00101 | 24-Mar-2026 | 13-Apr-2026 | COMP5-T-QELNG-SPM-00176 | 20-Apr-2026 | A-Approved/Reviewed with no comments
5 | PI | COMP5-SPM-PI-SDR-00004 | B | SPECIFICATION DEVIATION REQUEST FOR HYDROTESTING PRESSURE OF PIPES AT MANUFACTURER’S SHOP | Dolly Maria Mathew | 10-Mar-2026 | COMP5-T-SPM-QELNG-00101 | 24-Mar-2026 | 13-Apr-2026 | COMP5-T-QELNG-SPM-00176 | 20-Apr-2026 | A-Approved/Reviewed with no comments

## SDR REPLIED OPEN
SDR REPLIED OPEN ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 1 ¦ SDR REPLIED OPEN ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response
1 | EL | COMP5-SPM-EL-SDR-00010 | B | SPECIFICATION DEVIATION REQUEST FOR ELECTRICAL - SLD & SCHEMATICS DRAWING USING AUTOCAD | Vellapandian Kulasekaran | 07-Apr-2026 | COMP5-T-SPM-QELNG-00270 | 10-Apr-2026 | 30-Apr-2026 | COMP5-T-QELNG-SPM-00683 | 17-Jun-2026 | B-Approved/Reviewed with minor comments