## SUMMARY
TQ – TECHNICAL QUERY REGISTER ¦ COMP5 PROJECT SUMMARY
Report Date: 28 June 2026
TQ ISSUED (by Sai) | TQ NOT REPLIED (Not Expired) | TQ NOT REPLIED (Expired) | TQ REPLIED CLOSED | TQ REPLIED OPEN
54 | 10 | 0 | 31 | 13
DISCIPLINE BREAKDOWN
Discipline | ISSUED (by Sai) | NOT REPLIED (Not Exp.) | NOT REPLIED (Expired) | REPLIED CLOSED | REPLIED OPEN
Corrosion Engineering | 10 | 1 | 0 | 8 | 1
Electrical | 4 | 0 | 0 | 3 | 1
HVAC | 2 | 0 | 0 | 1 | 1
Mechanical | 2 | 0 | 0 | 2 | 0
Administrative / Eng. Mgmt | 4 | 1 | 0 | 2 | 1
Piping | 1 | 0 | 0 | 0 | 1
Process | 6 | 1 | 0 | 3 | 2
HSE&Q/LOSPE | 9 | 6 | 0 | 1 | 2
Structural | 15 | 1 | 0 | 10 | 4
Telecommunications | 1 | 0 | 0 | 1 | 0
TOTAL | 54 | 10 | 0 | 31 | 13

## TQ ISSUED (by Sai)
TQ ISSUED (BY SAI) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 54 ¦ TQ ISSUED (by Sai) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Doc Status
1 | CE | COMP5-SPM-CE-TQY-00005 | B | TECHNICAL QUERY FOR SOUR SERVICE - BACK WELDING REQUIREMENTS | Mihai Marius | 25-Feb-2026 | COMP5-T-SPM-QELNG-00022 | 26-Feb-2026 | 18-Mar-2026 | COMP5-T-QELNG-SPM-00031 | 11-Mar-2026 | A-Approved/Reviewed with no comments | Issued
2 | CE | COMP5-SPM-CE-TQY-00022 | B | TECHNICAL QUERY ON QUALIFICATION TESTING OF NON-METALLIC MATERIALS AS PER FEED SOUR SERVICE SPECIFICATION | Venkateswaran Viswanathan | 12-Mar-2026 | COMP5-T-SPM-QELNG-00054 | 16-Mar-2026 | 05-Apr-2026 | COMP5-T-QELNG-SPM-00063 | 25-Mar-2026 | A-Approved/Reviewed with no comments | Issued
3 | CE | COMP5-SPM-CE-TQY-00026 | B | TECHNICAL QUERY FOR PIPE DELIVERY CONDITIONS | Mihai Marius | 25-Mar-2026 | COMP5-T-SPM-QELNG-00113 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00097 | 05-Apr-2026 | A-Approved/Reviewed with no comments | Issued
4 | CE | COMP5-SPM-CE-TQY-00030 | C | TECHNICAL QUERY FOR APPLICABILITY OF THE REQUIREMENT FOR RT FOR THE ENDS OF OVERLAID PIPE AND COMPONENTS | Venkateswaran Viswanathan | 11-May-2026 | COMP5-T-SPM-QELNG-00605 | 11-May-2026 | 31-May-2026 | COMP5-T-QELNG-SPM-00646 | 14-Jun-2026 | A-Approved/Reviewed with no comments | Issued
5 | CE | COMP5-SPM-CE-TQY-00031 | B | TECHNICAL QUERY FOR PSL2 API 5L CS CLAD WELDED PIPES: BACKING MATERIAL - Q & T DELIVERY CONDITION | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00225 | 06-Apr-2026 | 26-Apr-2026 | COMP5-T-QELNG-SPM-00325 | 05-May-2026 | A-Approved/Reviewed with no comments | Issued
6 | CE | COMP5-SPM-CE-TQY-00032 | B | TECHNICAL QUERY FOR PMI LIMITATION ON CLAD MATERIALS BELOW 10” | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00242 | 08-Apr-2026 | 28-Apr-2026 | COMP5-T-QELNG-SPM-00333 | 06-May-2026 | A-Approved/Reviewed with no comments | Issued
7 | CE | COMP5-SPM-CE-TQY-00033 | B | TECHNICAL QUERY FOR SURFACE NDE REQUIREMENTS FOR SMLS PIPES | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00192 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00302 | 04-May-2026 | A-Approved/Reviewed with no comments | Issued
8 | CE | COMP5-SPM-CE-TQY-00034 | B | TECHNICAL QUERY FOR UT REQUIREMENTS FOR THE INCONEL B705 N06625 GRADE 1 | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00242 | 08-Apr-2026 | 28-Apr-2026 | COMP5-T-QELNG-SPM-00326 | 05-May-2026 | A-Approved/Reviewed with no comments | Issued
9 | CE | COMP5-SPM-CE-TQY-00059 | B | TECHNICAL QUERY FOR THE UPGRADE OF PIPING MATERIAL OF CONSTRUCTION FOR HP/LP FLARE IGNITION AND PILOT LINES | Venkateswaran Viswanathan | 06-May-2026 | COMP5-T-SPM-QELNG-00563 | 07-May-2026 | 27-May-2026 | COMP5-T-QELNG-SPM-00686 | 17-Jun-2026 | D-Rejected | Issued
10 | CE | COMP5-SPM-CE-TQY-00086 | B | TECHNICAL QUERRY FOR GRADE 60/65 FITTINGS AND FLANGES DELIVERY CONDITION | Mihai Marius | 12-Jun-2026 | COMP5-T-SPM-QELNG-01040 | 22-Jun-2026 | 09-Jul-2026 |  |  |  | Issued
11 | EL | COMP5-SPM-EL-TQY-00041 | B | TECHNICAL QUERY FOR USING DIALUX EVO SOFTWARE FOR ILLUMINATION CALCULATION | Munjuluru Kiran Kumar | 08-Apr-2026 | COMP5-T-SPM-QELNG-00281 | 12-Apr-2026 | 02-May-2026 | COMP5-T-QELNG-SPM-00241 | 27-Apr-2026 | A-Approved/Reviewed with no comments | Issued
12 | EL | COMP5-SPM-EL-TQY-00049 | B | TECHNICAL QUERY FOR GAP ANALYSIS BETWEEN ITT & COMP2 SPECIFICATIONS | Munjuluru Kiran Kumar | 12-Apr-2026 | COMP5-T-SPM-QELNG-00302 | 14-Apr-2026 | 04-May-2026 | COMP5-T-QELNG-SPM-00240 | 27-Apr-2026 | A-Approved/Reviewed with no comments | Issued
13 | EL | COMP5-SPM-EL-TQY-00050 | B | TECHNICAL QUERY FOR BUNCHING OF MORE THAN 2 LAYERS OF SMALL POWER AND CONTROL CABLES | Gundu Adi Seetaramaiah | 12-Apr-2026 | COMP5-T-SPM-QELNG-00667 | 17-May-2026 | 06-Jun-2026 | COMP5-T-QELNG-SPM-00685 | 17-Jun-2026 | A-Approved/Reviewed with no comments | Issued
14 | EL | COMP5-SPM-EL-TQY-00054 | B | TECHNICAL QUERY FOR REQUIREMENT OF LOCAL CONTROL STATION (LCS) AT RESPECTIVE MOTORS | Konar Esakkidas Esakki | 22-Apr-2026 | COMP5-T-SPM-QELNG-00477 | 30-Apr-2026 | 20-May-2026 | COMP5-T-QELNG-SPM-00327 | 05-May-2026 | C-Returned with comments | Issued
15 | HV | COMP5-SPM-HV-TQY-00006 | B | TECHNICAL QUERY FOR USE OF R407C REFRIGERANT FOR CP TECHNICAL BUILDING (CP4S AND CP6N) | Raffi Mohammad | 03-Feb-2026 | COMP5-T-SPM-QELNG-00030 | 04-Mar-2026 | 24-Mar-2026 | COMP5-T-QELNG-SPM-00080 | 30-Mar-2026 | D-Rejected | Issued
16 | HV | COMP5-SPM-HV-TQY-00039 | B | TECHNICAL QUERY FOR INGRESS PROTECTION FOR ELECTRICAL FITTINGS INSIDE AHU | Maruthakutti Balraj | 01-Apr-2026 | COMP5-T-SPM-QELNG-00280 | 12-Apr-2026 | 02-May-2026 | COMP5-T-QELNG-SPM-00349 | 10-May-2026 | A-Approved/Reviewed with no comments | Issued
17 | ME | COMP5-SPM-ME-TQY-00007 | B | TECHNICAL QUERY FOR CONFIRMATION REQUIRED ON LQ4S AND LQ6N PEDESTAL CRANE CAPACITY & WORKING RADIUS DESIGN/SELECTION | Kannan Israel Joseph | 04-Feb-2026 | COMP5-T-SPM-QELNG-00034 | 09-Mar-2026 | 29-Mar-2026 | COMP5-T-QELNG-SPM-00085 | 31-Mar-2026 | A-Approved/Reviewed with no comments | Issued
18 | ME | COMP5-SPM-ME-TQY-00008 | C | TECHNICAL QUERY FOR SEAWATER FILTER PACKAGE CONFIGURATION: 3 x 50% (2W+1S) INSTEAD OF 4 X 33% (3W+1S) |  |  | COMP5-T-SPM-QELNG-00362 | 20-Apr-2026 | 10-May-2026 | COMP5-T-QELNG-SPM-00297 | 03-May-2026 | A-Approved/Reviewed with no comments | Issued
19 | PE | COMP5-SPM-PE-TQY-00001 | B | TECHNICAL QUERY FOR ALIGNMENT OF SOFTWARE TO BE USED FOR NFPS-COMP5 PROJECT | Pandi Senthilkumar |  | COMP5-T-SPM-QELNG-00090 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00173 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
20 | PE | COMP5-SPM-PE-TQY-00002 | B | TECHNICAL QUERY FOR ALIGNMENT ON THE DOCUMENT NUMBERING ON NFPS-COMP5 PROJECT | Pandi Senthilkumar |  | COMP5-T-SPM-QELNG-00019 | 26-Feb-2026 | 18-Mar-2026 | COMP5-T-QELNG-SPM-00122 | 12-Apr-2026 | A-Approved/Reviewed with no comments | Issued
21 | PE | COMP5-SPM-PE-TQY-00029 | B | TECHNICAL QUERY FOR PROPOSAL FOR DOCUMENT REVISION AND SUBMISSION PHILOSOPHY | Maiti Sandeep | 25-Mar-2026 | COMP5-T-SPM-QELNG-00202 | 02-Apr-2026 | 22-Apr-2026 | COMP5-T-QELNG-SPM-00303 | 04-May-2026 | A-Approved/Reviewed with no comments | Issued
22 | PE | COMP5-SPM-PE-TQY-00051 | B | TECHNICAL QUERY FOR PROPOSAL ON THE EXCLUSIONS OF IFR REVISIONS ON THE SELECTED DELIVERABLES | Diyana | 16-Apr-2026 | COMP5-T-SPM-QELNG-00913 | 12-Jun-2026 | 02-Jul-2026 |  |  |  | Issued
23 | PI | COMP5-SPM-PI-TQY-00028 | B | TECHNICAL QUERY FOR MANUAL VALVE TEMPORARY FLUSHING SKID ARRANGEMENT | Saravanan Rajendran V | 25-Mar-2026 | COMP5-T-SPM-QELNG-00126 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00174 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
24 | PR | COMP5-SPM-PR-TQY-00023 | C | TECHNICAL QUERY FOR FINALIZATION OF IA, N2 QUANTITY | Nath Kedar |  | COMP5-T-SPM-QELNG-01001 | 18-Jun-2026 | 08-Jul-2026 | COMP5-T-QELNG-SPM-00729 | 23-Jun-2026 | A-Approved/Reviewed with no comments | Issued
25 | PR | COMP5-SPM-PR-TQY-00035 | B | TECHNICAL QUERY FOR PROPOSAL FOR OPTIMIZED PID REVISION CYCLE FOR CP6N COMPLEX GF | Nagarajan Manikandan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00167 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00157 | 16-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
26 | PR | COMP5-SPM-PR-TQY-00036 | B | TECHNICAL QUERY FOR CLARIFICATION REGARDING INTRAFIELD PIPELINES FROM RP5N TO RP6N | Gajula Vinayraj | 29-Mar-2026 | COMP5-T-SPM-QELNG-00165 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00202 | 22-Apr-2026 | I-No Review | Issued
27 | PR | COMP5-SPM-PR-TQY-00037 | B | TECHNICAL QUERY FOR FLOW ASSURANCE SOFTWARE VERSION | FERRI Domenico | 30-Mar-2026 | COMP5-T-SPM-QELNG-00297 | 13-Apr-2026 | 03-May-2026 | COMP5-T-QELNG-SPM-00177 | 20-Apr-2026 | A-Approved/Reviewed with no comments | Issued
28 | PR | COMP5-SPM-PR-TQY-00067 | B | TECHNICAL QUERY FOR PLANT AIR OPERATING CONDITION | Akbar Ali Moosa | 11-May-2026 | COMP5-T-SPM-QELNG-01009 | 18-Jun-2026 | 08-Jul-2026 |  |  |  | Issued
29 | PR | COMP5-SPM-PR-TQY-00078 | B | TECHNICAL QUERY FOR FA SIMULATION CASES | FERRI Domenico | 13-May-2026 | COMP5-T-SPM-QELNG-00885 | 10-Jun-2026 | 30-Jun-2026 | COMP5-T-QELNG-SPM-00665 | 15-Jun-2026 | A-Approved/Reviewed with no comments | Issued
30 | SH | COMP5-SPM-SH-TQY-00012 | B | TECHNICAL QUERY FOR CLEAN AGENT SYSTEM FULL DISCHARGE TEST | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-01057 | 23-Jun-2026 | 13-Jul-2026 |  |  |  | Issued
31 | SH | COMP5-SPM-SH-TQY-00013 | B | TECHNICAL QUERY FOR FIREWATER ISOLATION VALVES | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-00191 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00178 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
32 | SH | COMP5-SPM-SH-TQY-00014 | C | TECHNICAL QUERY FOR REQUIREMENT OF THE FOAM MAKER UNIT FOR THE HELIFUEL PACKAGE | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-01057 | 23-Jun-2026 | 13-Jul-2026
33 | SH | COMP5-SPM-SH-TQY-00015 | C | TECHNICAL QUERY FOR SPARE QUANTITY FOR FIRE EXTINGUISHERS | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued
34 | SH | COMP5-SPM-SH-TQY-00016 | C | TECHNICAL QUERY FOR ACTIVATION OF CLEAN AGENT SYSTEM BY HSSD | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued
35 | SH | COMP5-SPM-SH-TQY-00017 | B | TECHNICAL QUERY FOR VELOCITY CRITERIA FOR FIREWATER PIPING | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-00191 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00178 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
36 | SH | COMP5-SPM-SH-TQY-00018 | C | TECHNICAL QUERY FOR FIREWATER MONITOR REQUIREMENT | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued
37 | SH | COMP5-SPM-SH-TQY-00063 | B | TECHNICAL QUERY FOR SHIP COLLISION STUDY (VESSEL DETAILS) & MANNING DATA FOR RISK ASSESSMENT | Promtong Kasidit | 11-May-2026 | COMP5-T-SPM-QELNG-00867 | 10-Jun-2026 | 30-Jun-2026 | COMP5-T-QELNG-SPM-00691 | 18-Jun-2026 | A-Approved/Reviewed with no comments | Issued
38 | SH | COMP5-SPM-SH-TQY-00080 | B | TECHNICAL QUERY FOR DIFFS SYSTEM ACTIVATION LOGIC AUTOMATIC OR MANUAL | Arunkumar Arumugam | 19-May-2026 | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued
39 | ST | COMP5-SPM-ST-TQY-00004 | B | TECHNICAL QUERY FOR J-TUBES ARRANGEMENTS FOR CP4S AND CP6N COMPLEXES | Alonzo Vincenzo | 20-Feb-2026 | COMP5-T-SPM-QELNG-00182 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00363 | 11-May-2026 | A-Approved/Reviewed with no comments | Issued
40 | ST | COMP5-SPM-ST-TQY-00009 | B | TECHNICAL QUERY FOR THE REQUIREMENT FOR COLD VERSUS HOT FORMING | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00277 | 30-Apr-2026 | A-Approved/Reviewed with no comments | Issued
41 | ST | COMP5-SPM-ST-TQY-00010 | B | TECHNICAL QUERY FOR UPPER LIMITIATION FOR DIAMETER OF SEAMLESS PIPE MATERIAL | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00277 | 30-Apr-2026 | A-Approved/Reviewed with no comments | Issued
42 | ST | COMP5-SPM-ST-TQY-00011 | B | TECHNICAL QUERY FOR THE USE OF HIGHER CVN CLASS MATERIAL FOR REPLACING THE LOWER CVN CLASS | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00297 | 03-May-2026 | A-Approved/Reviewed with no comments | Issued
43 | ST | COMP5-SPM-ST-TQY-00024 | C | TECHNICAL QUERY FOR WATER DEPTH CONFIRMATION | Vincenzo Alonzo |  | COMP5-T-SPM-QELNG-00903 | 10-Jun-2026 | 30-Jun-2026 |  |  |  | Issued
44 | ST | COMP5-SPM-ST-TQY-00027 | B | TECHNICAL QUERY FOR CATHODIC PROTECTION SYSTEM - SACRIFICAL ANODES ALTERNATIVE METHODS FOR CHEMICAL ANALYSES - SPARK EMISSION SPECTROSCOPY | Filiberti Chiara | 25-Mar-2026 | COMP5-T-SPM-QELNG-00182 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00219 | 26-Apr-2026 | A-Approved/Reviewed with no comments | Issued
45 | ST | COMP5-SPM-ST-TQY-00038 | B | TECHNICAL QUERY FOR REQUEST APPROVAL TO USE SS316 BOLTS FOR SIZES BELOW 1/2″ IN LIEU OF ASTM A325 BOLTS & NUTS | Andoko Wijayanto | 01-Apr-2026 | COMP5-T-SPM-QELNG-00647 | 14-May-2026 | 03-Jun-2026 | COMP5-T-QELNG-SPM-00630 | 09-Jun-2026 | A-Approved/Reviewed with no comments | Issued
46 | ST | COMP5-SPM-ST-TQY-00043 | B | TECHNICAL QUERY FOR USE OF NON-COMPACT PLATE GIRDER SECTIONS | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00717 | 22-Jun-2026 | A-Approved/Reviewed with no comments | Issued
47 | ST | COMP5-SPM-ST-TQY-00044 | B | TECHNICAL QUERY FOR USE OF DUPLEX STEEL HILTI FASTENERS IN SPLASH AND WAVE ZONE | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00609 | 07-Jun-2026 | A-Approved/Reviewed with no comments | Issued
48 | ST | COMP5-SPM-ST-TQY-00045 | B | TECHNICAL QUERY FOR MINIMUM WEB THICKNESS FOR INTERNAL SECONDARY MEMBERS | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00537 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued
49 | ST | COMP5-SPM-ST-TQY-00046 | B | TECHNICAL QUERY FOR PROPOSAL OF COPE/RAT HOLE TO FACILITATE THE WELDING DURING FABRICATION OF GIRDERS/BEAMS AND NODES FOR NFPS COMP5 PROJECT | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00679 | 15-Jun-2026 | D-Rejected | Issued
50 | ST | COMP5-SPM-ST-TQY-00047 | B | TECHNICAL QUERY FOR SIGNLE - VEE BUTT JOINT FOR PIPE GREATER THAN/EQUAL TO 914.4MM DIAMETER FOR NFPS COMP5 PROJECT. | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00608 | 07-Jun-2026 | D-Rejected | Issued
51 | ST | COMP5-SPM-ST-TQY-00048 | B | TECHNICAL QUERY FOR REQUEST FOR APPROVAL TO OMIT VENT HOLES IN HANDLING PADEYES FOR CP4S AND CP6N | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00608 | 07-Jun-2026 | D-Rejected | Issued
52 | ST | COMP5-SPM-ST-TQY-00052 | B | TECHNICAL QUERY FOR SUBSIDENCE SENSITIVITY STUDY | Vincenzo Alonzo |  | COMP5-T-SPM-QELNG-00397 | 22-Apr-2026 | 12-May-2026 | COMP5-T-QELNG-SPM-00542 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued
53 | ST | COMP5-SPM-ST-TQY-00074 | B | TECHNICAL QUERY FOR TRIPOD PERMANENT INSPECTION PLATFORMS | Andrea Mariani | 11-May-2026 | COMP5-T-SPM-QELNG-00758 | 01-Jun-2026 | 21-Jun-2026 | COMP5-T-QELNG-SPM-00721 | 23-Jun-2026 | D-Rejected | Issued
54 | TC | COMP5-SPM-TC-TQY-00055 | B | TECHNICAL QUERY FOR PAGA SYSTEM HARMONIZATION IN CP6N COMPLEX | Mohammed Abdul Shadab Ahmer | 04-May-2026 | COMP5-T-SPM-QELNG-00556 | 06-May-2026 | 26-May-2026 | COMP5-T-QELNG-SPM-00539 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued

## TQ NOT REPLIED (Not Expired)
TQ NOT REPLIED (NOT EXPIRED) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 10 ¦ TQ NOT REPLIED (Not Expired) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Doc Status | Days Remaining
1 | CE | COMP5-SPM-CE-TQY-00086 | B | TECHNICAL QUERRY FOR GRADE 60/65 FITTINGS AND FLANGES DELIVERY CONDITION | Mihai Marius | 12-Jun-2026 | COMP5-T-SPM-QELNG-01040 | 22-Jun-2026 | 09-Jul-2026 |  |  |  | Issued | 11 days
2 | PE | COMP5-SPM-PE-TQY-00051 | B | TECHNICAL QUERY FOR PROPOSAL ON THE EXCLUSIONS OF IFR REVISIONS ON THE SELECTED DELIVERABLES | Diyana | 16-Apr-2026 | COMP5-T-SPM-QELNG-00913 | 12-Jun-2026 | 02-Jul-2026 |  |  |  | Issued | 4 days
3 | PR | COMP5-SPM-PR-TQY-00067 | B | TECHNICAL QUERY FOR PLANT AIR OPERATING CONDITION | Akbar Ali Moosa | 11-May-2026 | COMP5-T-SPM-QELNG-01009 | 18-Jun-2026 | 08-Jul-2026 |  |  |  | Issued | 10 days
4 | SH | COMP5-SPM-SH-TQY-00012 | B | TECHNICAL QUERY FOR CLEAN AGENT SYSTEM FULL DISCHARGE TEST | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-01057 | 23-Jun-2026 | 13-Jul-2026 |  |  |  | Issued | 15 days
5 | SH | COMP5-SPM-SH-TQY-00014 | C | TECHNICAL QUERY FOR REQUIREMENT OF THE FOAM MAKER UNIT FOR THE HELIFUEL PACKAGE | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-01057 | 23-Jun-2026 | 13-Jul-2026 |  |  |  |  | 15 days
6 | SH | COMP5-SPM-SH-TQY-00015 | C | TECHNICAL QUERY FOR SPARE QUANTITY FOR FIRE EXTINGUISHERS | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued | 6 days
7 | SH | COMP5-SPM-SH-TQY-00016 | C | TECHNICAL QUERY FOR ACTIVATION OF CLEAN AGENT SYSTEM BY HSSD | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued | 6 days
8 | SH | COMP5-SPM-SH-TQY-00018 | C | TECHNICAL QUERY FOR FIREWATER MONITOR REQUIREMENT | Arunkumar Arumugam |  | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued | 6 days
9 | SH | COMP5-SPM-SH-TQY-00080 | B | TECHNICAL QUERY FOR DIFFS SYSTEM ACTIVATION LOGIC AUTOMATIC OR MANUAL | Arunkumar Arumugam | 19-May-2026 | COMP5-T-SPM-QELNG-00886 | 14-Jun-2026 | 04-Jul-2026 |  |  |  | Issued | 6 days
10 | ST | COMP5-SPM-ST-TQY-00024 | C | TECHNICAL QUERY FOR WATER DEPTH CONFIRMATION | Vincenzo Alonzo |  | COMP5-T-SPM-QELNG-00903 | 10-Jun-2026 | 30-Jun-2026 |  |  |  | Issued | 2 days

## TQ NOT REPLIED (Expired)
TQ NOT REPLIED (EXPIRED) ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 0 ¦ TQ NOT REPLIED (Expired) ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Doc Status | Days Remaining
No records for this category

## TQ REPLIED CLOSED
TQ REPLIED CLOSED ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 31 ¦ TQ REPLIED CLOSED ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Doc Status
1 | CE | COMP5-SPM-CE-TQY-00005 | B | TECHNICAL QUERY FOR SOUR SERVICE - BACK WELDING REQUIREMENTS | Mihai Marius | 25-Feb-2026 | COMP5-T-SPM-QELNG-00022 | 26-Feb-2026 | 18-Mar-2026 | COMP5-T-QELNG-SPM-00031 | 11-Mar-2026 | A-Approved/Reviewed with no comments | Issued
2 | CE | COMP5-SPM-CE-TQY-00022 | B | TECHNICAL QUERY ON QUALIFICATION TESTING OF NON-METALLIC MATERIALS AS PER FEED SOUR SERVICE SPECIFICATION | Venkateswaran Viswanathan | 12-Mar-2026 | COMP5-T-SPM-QELNG-00054 | 16-Mar-2026 | 05-Apr-2026 | COMP5-T-QELNG-SPM-00063 | 25-Mar-2026 | A-Approved/Reviewed with no comments | Issued
3 | CE | COMP5-SPM-CE-TQY-00026 | B | TECHNICAL QUERY FOR PIPE DELIVERY CONDITIONS | Mihai Marius | 25-Mar-2026 | COMP5-T-SPM-QELNG-00113 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00097 | 05-Apr-2026 | A-Approved/Reviewed with no comments | Issued
4 | CE | COMP5-SPM-CE-TQY-00030 | C | TECHNICAL QUERY FOR APPLICABILITY OF THE REQUIREMENT FOR RT FOR THE ENDS OF OVERLAID PIPE AND COMPONENTS | Venkateswaran Viswanathan | 11-May-2026 | COMP5-T-SPM-QELNG-00605 | 11-May-2026 | 31-May-2026 | COMP5-T-QELNG-SPM-00646 | 14-Jun-2026 | A-Approved/Reviewed with no comments | Issued
5 | CE | COMP5-SPM-CE-TQY-00031 | B | TECHNICAL QUERY FOR PSL2 API 5L CS CLAD WELDED PIPES: BACKING MATERIAL - Q & T DELIVERY CONDITION | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00225 | 06-Apr-2026 | 26-Apr-2026 | COMP5-T-QELNG-SPM-00325 | 05-May-2026 | A-Approved/Reviewed with no comments | Issued
6 | CE | COMP5-SPM-CE-TQY-00032 | B | TECHNICAL QUERY FOR PMI LIMITATION ON CLAD MATERIALS BELOW 10” | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00242 | 08-Apr-2026 | 28-Apr-2026 | COMP5-T-QELNG-SPM-00333 | 06-May-2026 | A-Approved/Reviewed with no comments | Issued
7 | CE | COMP5-SPM-CE-TQY-00033 | B | TECHNICAL QUERY FOR SURFACE NDE REQUIREMENTS FOR SMLS PIPES | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00192 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00302 | 04-May-2026 | A-Approved/Reviewed with no comments | Issued
8 | CE | COMP5-SPM-CE-TQY-00034 | B | TECHNICAL QUERY FOR UT REQUIREMENTS FOR THE INCONEL B705 N06625 GRADE 1 | Venkateswaran Viswanathan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00242 | 08-Apr-2026 | 28-Apr-2026 | COMP5-T-QELNG-SPM-00326 | 05-May-2026 | A-Approved/Reviewed with no comments | Issued
9 | EL | COMP5-SPM-EL-TQY-00041 | B | TECHNICAL QUERY FOR USING DIALUX EVO SOFTWARE FOR ILLUMINATION CALCULATION | Munjuluru Kiran Kumar | 08-Apr-2026 | COMP5-T-SPM-QELNG-00281 | 12-Apr-2026 | 02-May-2026 | COMP5-T-QELNG-SPM-00241 | 27-Apr-2026 | A-Approved/Reviewed with no comments | Issued
10 | EL | COMP5-SPM-EL-TQY-00049 | B | TECHNICAL QUERY FOR GAP ANALYSIS BETWEEN ITT & COMP2 SPECIFICATIONS | Munjuluru Kiran Kumar | 12-Apr-2026 | COMP5-T-SPM-QELNG-00302 | 14-Apr-2026 | 04-May-2026 | COMP5-T-QELNG-SPM-00240 | 27-Apr-2026 | A-Approved/Reviewed with no comments | Issued
11 | EL | COMP5-SPM-EL-TQY-00050 | B | TECHNICAL QUERY FOR BUNCHING OF MORE THAN 2 LAYERS OF SMALL POWER AND CONTROL CABLES | Gundu Adi Seetaramaiah | 12-Apr-2026 | COMP5-T-SPM-QELNG-00667 | 17-May-2026 | 06-Jun-2026 | COMP5-T-QELNG-SPM-00685 | 17-Jun-2026 | A-Approved/Reviewed with no comments | Issued
12 | HV | COMP5-SPM-HV-TQY-00039 | B | TECHNICAL QUERY FOR INGRESS PROTECTION FOR ELECTRICAL FITTINGS INSIDE AHU | Maruthakutti Balraj | 01-Apr-2026 | COMP5-T-SPM-QELNG-00280 | 12-Apr-2026 | 02-May-2026 | COMP5-T-QELNG-SPM-00349 | 10-May-2026 | A-Approved/Reviewed with no comments | Issued
13 | ME | COMP5-SPM-ME-TQY-00007 | B | TECHNICAL QUERY FOR CONFIRMATION REQUIRED ON LQ4S AND LQ6N PEDESTAL CRANE CAPACITY & WORKING RADIUS DESIGN/SELECTION | Kannan Israel Joseph | 04-Feb-2026 | COMP5-T-SPM-QELNG-00034 | 09-Mar-2026 | 29-Mar-2026 | COMP5-T-QELNG-SPM-00085 | 31-Mar-2026 | A-Approved/Reviewed with no comments | Issued
14 | ME | COMP5-SPM-ME-TQY-00008 | C | TECHNICAL QUERY FOR SEAWATER FILTER PACKAGE CONFIGURATION: 3 x 50% (2W+1S) INSTEAD OF 4 X 33% (3W+1S) |  |  | COMP5-T-SPM-QELNG-00362 | 20-Apr-2026 | 10-May-2026 | COMP5-T-QELNG-SPM-00297 | 03-May-2026 | A-Approved/Reviewed with no comments | Issued
15 | PE | COMP5-SPM-PE-TQY-00002 | B | TECHNICAL QUERY FOR ALIGNMENT ON THE DOCUMENT NUMBERING ON NFPS-COMP5 PROJECT | Pandi Senthilkumar |  | COMP5-T-SPM-QELNG-00019 | 26-Feb-2026 | 18-Mar-2026 | COMP5-T-QELNG-SPM-00122 | 12-Apr-2026 | A-Approved/Reviewed with no comments | Issued
16 | PE | COMP5-SPM-PE-TQY-00029 | B | TECHNICAL QUERY FOR PROPOSAL FOR DOCUMENT REVISION AND SUBMISSION PHILOSOPHY | Maiti Sandeep | 25-Mar-2026 | COMP5-T-SPM-QELNG-00202 | 02-Apr-2026 | 22-Apr-2026 | COMP5-T-QELNG-SPM-00303 | 04-May-2026 | A-Approved/Reviewed with no comments | Issued
17 | PR | COMP5-SPM-PR-TQY-00023 | C | TECHNICAL QUERY FOR FINALIZATION OF IA, N2 QUANTITY | Nath Kedar |  | COMP5-T-SPM-QELNG-01001 | 18-Jun-2026 | 08-Jul-2026 | COMP5-T-QELNG-SPM-00729 | 23-Jun-2026 | A-Approved/Reviewed with no comments | Issued
18 | PR | COMP5-SPM-PR-TQY-00037 | B | TECHNICAL QUERY FOR FLOW ASSURANCE SOFTWARE VERSION | FERRI Domenico | 30-Mar-2026 | COMP5-T-SPM-QELNG-00297 | 13-Apr-2026 | 03-May-2026 | COMP5-T-QELNG-SPM-00177 | 20-Apr-2026 | A-Approved/Reviewed with no comments | Issued
19 | PR | COMP5-SPM-PR-TQY-00078 | B | TECHNICAL QUERY FOR FA SIMULATION CASES | FERRI Domenico | 13-May-2026 | COMP5-T-SPM-QELNG-00885 | 10-Jun-2026 | 30-Jun-2026 | COMP5-T-QELNG-SPM-00665 | 15-Jun-2026 | A-Approved/Reviewed with no comments | Issued
20 | SH | COMP5-SPM-SH-TQY-00063 | B | TECHNICAL QUERY FOR SHIP COLLISION STUDY (VESSEL DETAILS) & MANNING DATA FOR RISK ASSESSMENT | Promtong Kasidit | 11-May-2026 | COMP5-T-SPM-QELNG-00867 | 10-Jun-2026 | 30-Jun-2026 | COMP5-T-QELNG-SPM-00691 | 18-Jun-2026 | A-Approved/Reviewed with no comments | Issued
21 | ST | COMP5-SPM-ST-TQY-00004 | B | TECHNICAL QUERY FOR J-TUBES ARRANGEMENTS FOR CP4S AND CP6N COMPLEXES | Alonzo Vincenzo | 20-Feb-2026 | COMP5-T-SPM-QELNG-00182 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00363 | 11-May-2026 | A-Approved/Reviewed with no comments | Issued
22 | ST | COMP5-SPM-ST-TQY-00009 | B | TECHNICAL QUERY FOR THE REQUIREMENT FOR COLD VERSUS HOT FORMING | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00277 | 30-Apr-2026 | A-Approved/Reviewed with no comments | Issued
23 | ST | COMP5-SPM-ST-TQY-00010 | B | TECHNICAL QUERY FOR UPPER LIMITIATION FOR DIAMETER OF SEAMLESS PIPE MATERIAL | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00277 | 30-Apr-2026 | A-Approved/Reviewed with no comments | Issued
24 | ST | COMP5-SPM-ST-TQY-00011 | B | TECHNICAL QUERY FOR THE USE OF HIGHER CVN CLASS MATERIAL FOR REPLACING THE LOWER CVN CLASS | Andoko Wijayanto | 10-Mar-2026 | COMP5-T-SPM-QELNG-00222 | 07-Apr-2026 | 27-Apr-2026 | COMP5-T-QELNG-SPM-00297 | 03-May-2026 | A-Approved/Reviewed with no comments | Issued
25 | ST | COMP5-SPM-ST-TQY-00027 | B | TECHNICAL QUERY FOR CATHODIC PROTECTION SYSTEM - SACRIFICAL ANODES ALTERNATIVE METHODS FOR CHEMICAL ANALYSES - SPARK EMISSION SPECTROSCOPY | Filiberti Chiara | 25-Mar-2026 | COMP5-T-SPM-QELNG-00182 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00219 | 26-Apr-2026 | A-Approved/Reviewed with no comments | Issued
26 | ST | COMP5-SPM-ST-TQY-00038 | B | TECHNICAL QUERY FOR REQUEST APPROVAL TO USE SS316 BOLTS FOR SIZES BELOW 1/2″ IN LIEU OF ASTM A325 BOLTS & NUTS | Andoko Wijayanto | 01-Apr-2026 | COMP5-T-SPM-QELNG-00647 | 14-May-2026 | 03-Jun-2026 | COMP5-T-QELNG-SPM-00630 | 09-Jun-2026 | A-Approved/Reviewed with no comments | Issued
27 | ST | COMP5-SPM-ST-TQY-00043 | B | TECHNICAL QUERY FOR USE OF NON-COMPACT PLATE GIRDER SECTIONS | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00717 | 22-Jun-2026 | A-Approved/Reviewed with no comments | Issued
28 | ST | COMP5-SPM-ST-TQY-00044 | B | TECHNICAL QUERY FOR USE OF DUPLEX STEEL HILTI FASTENERS IN SPLASH AND WAVE ZONE | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00609 | 07-Jun-2026 | A-Approved/Reviewed with no comments | Issued
29 | ST | COMP5-SPM-ST-TQY-00045 | B | TECHNICAL QUERY FOR MINIMUM WEB THICKNESS FOR INTERNAL SECONDARY MEMBERS | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00537 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued
30 | ST | COMP5-SPM-ST-TQY-00052 | B | TECHNICAL QUERY FOR SUBSIDENCE SENSITIVITY STUDY | Vincenzo Alonzo |  | COMP5-T-SPM-QELNG-00397 | 22-Apr-2026 | 12-May-2026 | COMP5-T-QELNG-SPM-00542 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued
31 | TC | COMP5-SPM-TC-TQY-00055 | B | TECHNICAL QUERY FOR PAGA SYSTEM HARMONIZATION IN CP6N COMPLEX | Mohammed Abdul Shadab Ahmer | 04-May-2026 | COMP5-T-SPM-QELNG-00556 | 06-May-2026 | 26-May-2026 | COMP5-T-QELNG-SPM-00539 | 01-Jun-2026 | A-Approved/Reviewed with no comments | Issued

## TQ REPLIED OPEN
TQ REPLIED OPEN ¦ COMP5 PROJECT ¦ 28 June 2026
Total Records: 13 ¦ TQ REPLIED OPEN ¦ Date: 28 June 2026
# | Discipline | Document Number | Rev. | Title | Responsible Engineer | Date Requested | Transmittal to CPY | Date Issued to CPY | Due Date | Transmittal from CPY | Date Replied | CPY Response | Doc Status
1 | CE | COMP5-SPM-CE-TQY-00059 | B | TECHNICAL QUERY FOR THE UPGRADE OF PIPING MATERIAL OF CONSTRUCTION FOR HP/LP FLARE IGNITION AND PILOT LINES | Venkateswaran Viswanathan | 06-May-2026 | COMP5-T-SPM-QELNG-00563 | 07-May-2026 | 27-May-2026 | COMP5-T-QELNG-SPM-00686 | 17-Jun-2026 | D-Rejected | Issued
2 | EL | COMP5-SPM-EL-TQY-00054 | B | TECHNICAL QUERY FOR REQUIREMENT OF LOCAL CONTROL STATION (LCS) AT RESPECTIVE MOTORS | Konar Esakkidas Esakki | 22-Apr-2026 | COMP5-T-SPM-QELNG-00477 | 30-Apr-2026 | 20-May-2026 | COMP5-T-QELNG-SPM-00327 | 05-May-2026 | C-Returned with comments | Issued
3 | HV | COMP5-SPM-HV-TQY-00006 | B | TECHNICAL QUERY FOR USE OF R407C REFRIGERANT FOR CP TECHNICAL BUILDING (CP4S AND CP6N) | Raffi Mohammad | 03-Feb-2026 | COMP5-T-SPM-QELNG-00030 | 04-Mar-2026 | 24-Mar-2026 | COMP5-T-QELNG-SPM-00080 | 30-Mar-2026 | D-Rejected | Issued
4 | PE | COMP5-SPM-PE-TQY-00001 | B | TECHNICAL QUERY FOR ALIGNMENT OF SOFTWARE TO BE USED FOR NFPS-COMP5 PROJECT | Pandi Senthilkumar |  | COMP5-T-SPM-QELNG-00090 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00173 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
5 | PI | COMP5-SPM-PI-TQY-00028 | B | TECHNICAL QUERY FOR MANUAL VALVE TEMPORARY FLUSHING SKID ARRANGEMENT | Saravanan Rajendran V | 25-Mar-2026 | COMP5-T-SPM-QELNG-00126 | 26-Mar-2026 | 15-Apr-2026 | COMP5-T-QELNG-SPM-00174 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
6 | PR | COMP5-SPM-PR-TQY-00035 | B | TECHNICAL QUERY FOR PROPOSAL FOR OPTIMIZED PID REVISION CYCLE FOR CP6N COMPLEX GF | Nagarajan Manikandan | 25-Mar-2026 | COMP5-T-SPM-QELNG-00167 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00157 | 16-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
7 | PR | COMP5-SPM-PR-TQY-00036 | B | TECHNICAL QUERY FOR CLARIFICATION REGARDING INTRAFIELD PIPELINES FROM RP5N TO RP6N | Gajula Vinayraj | 29-Mar-2026 | COMP5-T-SPM-QELNG-00165 | 31-Mar-2026 | 20-Apr-2026 | COMP5-T-QELNG-SPM-00202 | 22-Apr-2026 | I-No Review | Issued
8 | SH | COMP5-SPM-SH-TQY-00013 | B | TECHNICAL QUERY FOR FIREWATER ISOLATION VALVES | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-00191 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00178 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
9 | SH | COMP5-SPM-SH-TQY-00017 | B | TECHNICAL QUERY FOR VELOCITY CRITERIA FOR FIREWATER PIPING | Arunkumar Arumugam | 10-Mar-2026 | COMP5-T-SPM-QELNG-00191 | 01-Apr-2026 | 21-Apr-2026 | COMP5-T-QELNG-SPM-00178 | 20-Apr-2026 | B-Approved/Reviewed with minor comments | Issued
10 | ST | COMP5-SPM-ST-TQY-00046 | B | TECHNICAL QUERY FOR PROPOSAL OF COPE/RAT HOLE TO FACILITATE THE WELDING DURING FABRICATION OF GIRDERS/BEAMS AND NODES FOR NFPS COMP5 PROJECT | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00679 | 15-Jun-2026 | D-Rejected | Issued
11 | ST | COMP5-SPM-ST-TQY-00047 | B | TECHNICAL QUERY FOR SIGNLE - VEE BUTT JOINT FOR PIPE GREATER THAN/EQUAL TO 914.4MM DIAMETER FOR NFPS COMP5 PROJECT. | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00608 | 07-Jun-2026 | D-Rejected | Issued
12 | ST | COMP5-SPM-ST-TQY-00048 | B | TECHNICAL QUERY FOR REQUEST FOR APPROVAL TO OMIT VENT HOLES IN HANDLING PADEYES FOR CP4S AND CP6N | Ibrahim Ramy | 08-Apr-2026 | COMP5-T-SPM-QELNG-00384 | 21-Apr-2026 | 11-May-2026 | COMP5-T-QELNG-SPM-00608 | 07-Jun-2026 | D-Rejected | Issued
13 | ST | COMP5-SPM-ST-TQY-00074 | B | TECHNICAL QUERY FOR TRIPOD PERMANENT INSPECTION PLATFORMS | Andrea Mariani | 11-May-2026 | COMP5-T-SPM-QELNG-00758 | 01-Jun-2026 | 21-Jun-2026 | COMP5-T-QELNG-SPM-00721 | 23-Jun-2026 | D-Rejected | Issued